Post-Operative Exercise Tracker

Project Plan

Version 1.0

Prepared: March 5, 2026

Based on: Requirements v1.1 (approved) + Functional Specification v1.1 (approved)

Repo: https://github.com/perelgut/postopExerciseTracker

# 1. Project Overview

Total tasks: 42 across 5 phases. Estimated duration: 17 developer-days. Critical path runs through Firebase setup, data layer, logging screen, and deployment.

| Phase | Name | Tasks | Est. Days |
| --- | --- | --- | --- |
| Phase 1 | Phase 1 — Project Setup & Infrastructure | 9 | 5.5d |
| Phase 2 | Phase 2 — Data Layer | 9 | 10.0d |
| Phase 3 | Phase 3 — UI: Core Screens | 11 | 14.0d |
| Phase 4 | Phase 4 — Integration, Polish & Should Haves | 9 | 7.5d |
| Phase 5 | Phase 5 — Release & Handover | 4 | 2.0d |

Total estimate: 39.0 developer-days (serial). With parallelism, critical path delivers in 17 calendar days.

Critical path tasks are highlighted in red throughout this document and represent the minimum sequence that determines overall project duration.

# 2. Deliverables Schedule

| Deliverable | Description | Phase | Day Target | Req IDs |
| --- | --- | --- | --- | --- |
| Repository live | postopExerciseTracker repo on GitHub, GitHub Pages building | 1 | Day 2 | M-24 |
| Firebase ready | Project created, Firestore + Anonymous Auth configured, rules set | 1 | Day 2 | M-15,M-16 |
| exercises.js complete | All 11 exercises, all progressions, all descriptions authored and verified | 2 | Day 4 | M-01 to M-05 |
| Data layer complete | auth.js, firestore.js, scheduler.js, progression.js — tested | 2 | Day 7 | M-10 to M-18 |
| Logging screen working | screen-log renders today's exercises, accepts input, saves to Firestore | 3 | Day 12 | M-06 to M-09 |
| Progression screen working | screen-progressions renders all cards, Advance button saves to Firestore | 3 | Day 14 | M-12 to M-14 |
| History table working | screen-history renders 30-day table with correct cells and scroll | 3 | Day 15 | M-19 to M-22 |
| Should Haves complete | Recovery day, completion badge, offline support, edit log | 4 | Day 17 | S-01 to S-05 |
| Cross-browser tested | All target browsers/devices verified. Bugs fixed. | 4 | Day 19 | M-23 |
| PROTOTYPE LIVE | App deployed, smoke tested, patient handover complete | 5 | Day 20 | All M-reqs |

# 3. PERT Analysis

The following table shows each task with its duration, dependencies, earliest start, earliest finish, and critical path status. All durations are in developer-days. Critical path tasks (red) have zero float — any delay directly delays the prototype delivery date.

| Task ID | Task Name | Duration | Depends On | Early Start | Early Finish | Critical Path |
| --- | --- | --- | --- | --- | --- | --- |
| T1.1 | Create GitHub repository (postopExerciseTracker, pub... | 0.5d | — | 0.0d | 0.5d | CRITICAL |
| T1.2 | Set up GitHub Pages + deploy.yml GitHub Actions work... | 1d | T1.1 | 0.5d | 1.5d | CRITICAL |
| T1.3 | Create Firebase project (perelgut@gmail.com) | 0.5d | T1.1 | 0.5d | 1.0d | CRITICAL |
| T1.4 | Create Firestore database (northamerica-northeast2, ... | 0.5d | T1.3 | 1.0d | 1.5d | CRITICAL |
| T1.5 | Enable Firebase Anonymous Authentication | 0.5d | T1.3 | 1.0d | 1.5d | CRITICAL |
| T1.6 | Apply Firestore security rules | 0.5d | T1.4 | 1.5d | 2.0d | CRITICAL |
| T1.7 | Add Firebase config as GitHub Secrets; configure dep... | 1d | T1.2, T1.3 | 1.5d | 2.5d | CRITICAL |
| T1.8 | Create project directory structure and placeholder f... | 0.5d | T1.1 | 0.5d | 1.0d | — |
| T1.9 | Verify end-to-end deployment: push to main → GitHub ... | 0.5d | T1.7, T1.8 | 2.5d | 3.0d | CRITICAL |
| T2.1 | Author exercises.js — all 11 exercises, all progress... | 2d | T1.8 | 1.0d | 3.0d | CRITICAL |
| T2.2 | Author firebase-config.js with placeholder tokens | 0.5d | T1.7 | 2.5d | 3.0d | CRITICAL |
| T2.3 | Implement auth.js — Firebase Anonymous Auth, localSt... | 1d | T2.2 | 3.0d | 4.0d | CRITICAL |
| T2.4 | Implement firestore.js — all Firestore read/write fu... | 2d | T2.3 | 4.0d | 6.0d | CRITICAL |
| T2.5 | Implement scheduler.js — getApplicableExercises(), d... | 1d | T2.1 | 3.0d | 4.0d | CRITICAL |
| T2.6 | Implement progression.js — read/write progressions, ... | 1d | T2.4 | 6.0d | 7.0d | — |
| T2.7 | Unit test: scheduler.js (all 7 days, verify correct ... | 1d | T2.5 | 4.0d | 5.0d | CRITICAL |
| T2.8 | Unit test: progression.js (boundary values, max prog... | 0.5d | T2.6 | 7.0d | 7.5d | — |
| T2.9 | Integration test: auth + Firestore read/write round-... | 1d | T2.4 | 6.0d | 7.0d | CRITICAL |
| T3.1 | Implement index.html shell, CSS styles.css — mobile-... | 1d | T1.8 | 1.0d | 2.0d | CRITICAL |
| T3.2 | Implement ui.js — screen switching, toast notificati... | 1d | T3.1 | 2.0d | 3.0d | CRITICAL |
| T3.3 | Implement app.js — startup sequence (Steps 1–9 per S... | 1.5d | T2.4, T2.5, T3.2 | 6.0d | 7.5d | CRITICAL |
| T3.4 | Implement bottom navigation bar (Today / History / P... | 0.5d | T3.2 | 3.0d | 3.5d | — |
| T3.5 | Implement screen-log: exercise cards, expand/collaps... | 2d | T3.3, T2.1 | 7.5d | 9.5d | CRITICAL |
| T3.6 | Implement screen-log: time-of-day selector with devi... | 1d | T3.5 | 9.5d | 10.5d | — |
| T3.7 | Implement logger.js — log entry capture, validation,... | 1.5d | T3.5, T2.4 | 9.5d | 11.0d | CRITICAL |
| T3.8 | Implement edit/update existing log entry (same day) | 1d | T3.7 | 11.0d | 12.0d | — |
| T3.9 | Implement screen-progressions: all 11 cards, Advance... | 1.5d | T3.2, T2.6 | 7.0d | 8.5d | — |
| T3.10 | Implement history.js — 30-day table, sticky row head... | 2d | T3.2, T2.4, T2.5 | 6.0d | 8.0d | — |
| T3.11 | Implement css/table.css — table layout, cell formatt... | 1d | T3.10 | 8.0d | 9.0d | — |
| T4.1 | Recovery day counter — calculate and display 'Day N'... | 0.5d | T3.3 | 7.5d | 8.0d | — |
| T4.2 | Completion indicator — green/amber badge showing tod... | 0.5d | T3.7 | 11.0d | 11.5d | — |
| T4.3 | Offline banner — detect navigator.onLine, show/hide ... | 0.5d | T3.2 | 3.0d | 3.5d | — |
| T4.4 | Enable Firestore offline persistence (enablePersiste... | 0.5d | T2.4 | 6.0d | 6.5d | — |
| T4.5 | Cross-browser testing: iOS Safari, Android Chrome, D... | 1.5d | T3.10, T3.9, T3.7 | 11.0d | 12.5d | CRITICAL |
| T4.6 | Mobile layout review: 320px min-width, tap targets 4... | 1d | T4.5 | 12.5d | 13.5d | — |
| T4.7 | End-to-end functional test: full patient session fro... | 1d | T4.5 | 12.5d | 13.5d | CRITICAL |
| T4.8 | Bug fixes from T4.5–T4.7 testing | 1.5d | T4.7 | 13.5d | 15.0d | CRITICAL |
| T4.9 | Author README.md — setup instructions, Firebase conf... | 0.5d | T1.9 | 3.0d | 3.5d | — |
| T5.1 | Final deployment to GitHub Pages — verify live at pe... | 0.5d | T4.8 | 15.0d | 15.5d | CRITICAL |
| T5.2 | Smoke test on live deployed URL — all screens, all e... | 0.5d | T5.1 | 15.5d | 16.0d | CRITICAL |
| T5.3 | Patient handover — share URL, brief walkthrough of s... | 0.5d | T5.2 | 16.0d | 16.5d | CRITICAL |
| T5.4 | Archive project documents (Requirements, Spec, Proje... | 0.5d | T5.1 | 15.5d | 16.0d | — |

# 4. GANTT Chart

Each row is one task. Columns represent proportional time slots across the 17-day schedule. Red bars = critical path tasks. Blue/green/orange/purple/maroon = phase colour. Grey = not scheduled in that slot.

| Task | D1 | D2 | D3 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D9 | D10 | D11 | D12 | D13 | D14 | D14 | D15 | D16 | D17 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 — Project Setup & Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.1: Create GitHub repository (postopExerciseTracker, public) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.2: Set up GitHub Pages + deploy.yml GitHub Actions workflow |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.3: Create Firebase project (perelgut@gmail.com) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.4: Create Firestore database (northamerica-northeast2, Toronto) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.5: Enable Firebase Anonymous Authentication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.6: Apply Firestore security rules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.7: Add Firebase config as GitHub Secrets; configure deploy.yml injection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.8: Create project directory structure and placeholder files |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T1.9: Verify end-to-end deployment: push to main → GitHub Pages live |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2 — Data Layer |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.1: Author exercises.js — all 11 exercises, all progressions, all descriptions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.2: Author firebase-config.js with placeholder tokens |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.3: Implement auth.js — Firebase Anonymous Auth, localStorage UID fallback |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.4: Implement firestore.js — all Firestore read/write functions |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.5: Implement scheduler.js — getApplicableExercises(), day-of-week rules |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.6: Implement progression.js — read/write progressions, max validation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.7: Unit test: scheduler.js (all 7 days, verify correct exercise sets) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.8: Unit test: progression.js (boundary values, max progression enforcement) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T2.9: Integration test: auth + Firestore read/write round-trip |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 3 — UI: Core Screens |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.1: Implement index.html shell, CSS styles.css — mobile-first layout |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.2: Implement ui.js — screen switching, toast notifications, loading spinner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.3: Implement app.js — startup sequence (Steps 1–9 per Spec Sec 6.1) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.4: Implement bottom navigation bar (Today / History / Progress tabs) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.5: Implement screen-log: exercise cards, expand/collapse, frequency badges |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.6: Implement screen-log: time-of-day selector with device clock pre-selection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.7: Implement logger.js — log entry capture, validation, Firestore save |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.8: Implement edit/update existing log entry (same day) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.9: Implement screen-progressions: all 11 cards, Advance button, max guard |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.10: Implement history.js — 30-day table, sticky row header, horizontal scroll |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T3.11: Implement css/table.css — table layout, cell formatting, responsive scroll |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 4 — Integration, Polish & Should Haves |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.1: Recovery day counter — calculate and display 'Day N' on screen-log |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.2: Completion indicator — green/amber badge showing today's log status |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.3: Offline banner — detect navigator.onLine, show/hide amber banner |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.4: Enable Firestore offline persistence (enablePersistence()) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.5: Cross-browser testing: iOS Safari, Android Chrome, Desktop Chrome/Firefox/Edge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.6: Mobile layout review: 320px min-width, tap targets 44px, font sizes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.7: End-to-end functional test: full patient session from Day 1 through history view |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.8: Bug fixes from T4.5–T4.7 testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T4.9: Author README.md — setup instructions, Firebase config steps, repo overview |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 5 — Release & Handover |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.1: Final deployment to GitHub Pages — verify live at perelgut.github.io/postopExerciseTracker/ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.2: Smoke test on live deployed URL — all screens, all exercises, Firestore writes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.3: Patient handover — share URL, brief walkthrough of screens and progression management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| T5.4: Archive project documents (Requirements, Spec, Project Plan) to repo /docs folder |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

# 5. Task Detail Pages

Each task is documented on its own page below with: phase, requirements, dependencies, schedule, files changed, assumptions, and the AI prompt to use when implementing it. Total: 42 tasks.

| T1.1 | Create GitHub repository (postopExerciseTracker, public) | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-24 |
| Dependencies | None — can start immediately |
| Scheduled Start | Day 0.0 |
| Scheduled End | Day 0.5 |

Files Added / Changed

- Create: /postopExerciseTracker (GitHub repo)

Assumptions

perelgut GitHub account exists and is accessible. No existing repo named postopExerciseTracker.

AI Prompt for Implementation

Create a new public GitHub repository named 'postopExerciseTracker' under the account perelgut. The repository should be initialised with a README.md and a .gitignore for Node.js projects. Do not add any source files yet.

| T1.2 | Set up GitHub Pages + deploy.yml GitHub Actions workflow | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-24 |
| Dependencies | T1.1 |
| Scheduled Start | Day 0.5 |
| Scheduled End | Day 1.5 |

Files Added / Changed

- Add: .github/workflows/deploy.yml

- Edit: README.md (placeholder)

Assumptions

GitHub Actions is enabled for the account. peaceiris/actions-gh-pages@v4 is accessible.

AI Prompt for Implementation

Write a GitHub Actions workflow file at .github/workflows/deploy.yml that triggers on push to the main branch and deploys the repository root to GitHub Pages using the peaceiris/actions-gh-pages@v4 action. The workflow must first run a sed step to inject Firebase config values from GitHub Secrets into js/firebase-config.js before deploying. The secrets to inject are: FIREBASE_API_KEY, FIREBASE_AUTH_DOMAIN, FIREBASE_PROJECT_ID, FIREBASE_STORAGE_BUCKET, FIREBASE_MESSAGING_SENDER_ID, FIREBASE_APP_ID.

| T1.3 | Create Firebase project (perelgut@gmail.com) | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-15,M-16 |
| Dependencies | T1.1 |
| Scheduled Start | Day 0.5 |
| Scheduled End | Day 1.0 |

Files Added / Changed

- Firebase Console: new project

Assumptions

perelgut@gmail.com Google account is accessible. No existing Firebase project named postopExerciseTracker.

AI Prompt for Implementation

[Manual Firebase Console step — no AI prompt required] Go to https://console.firebase.google.com, sign in with perelgut@gmail.com, and create a new project named 'postopExerciseTracker'. Disable Google Analytics. Register a Web App named 'postop-tracker' and save the firebaseConfig object.

| T1.4 | Create Firestore database (northamerica-northeast2, Toronto) | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-15 |
| Dependencies | T1.3 |
| Scheduled Start | Day 1.0 |
| Scheduled End | Day 1.5 |

Files Added / Changed

- Firebase Console: Firestore DB — northamerica-northeast2

Assumptions

Firebase project from T1.3 exists. northamerica-northeast2 is available in the Firebase console.

AI Prompt for Implementation

[Manual Firebase Console step] In the Firebase project created in T1.3, go to Firestore Database → Create database → Production mode. Select region: northamerica-northeast2 (Toronto). WARNING: this selection is permanent and cannot be changed.

| T1.5 | Enable Firebase Anonymous Authentication | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-16 |
| Dependencies | T1.3 |
| Scheduled Start | Day 1.0 |
| Scheduled End | Day 1.5 |

Files Added / Changed

- Firebase Console: Auth → Anonymous → Enable

Assumptions

Firebase project from T1.3 exists.

AI Prompt for Implementation

[Manual Firebase Console step] In the Firebase project, go to Authentication → Sign-in method → Anonymous → Enable. Save.

| T1.6 | Apply Firestore security rules | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-15,M-16 |
| Dependencies | T1.4 |
| Scheduled Start | Day 1.5 |
| Scheduled End | Day 2.0 |

Files Added / Changed

- Firebase Console: Firestore Rules — paste rules from Spec Sec 8.2

Assumptions

Firestore database from T1.4 exists.

AI Prompt for Implementation

In the Firebase project Firestore console, go to Rules and replace the default rules with the following security rules that allow a user to read and write only their own data scoped by their anonymous UID: [paste rules from Functional Specification Section 8.2].

| T1.7 | Add Firebase config as GitHub Secrets; configure deploy.yml injection | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-24 |
| Dependencies | T1.2, T1.3 |
| Scheduled Start | Day 1.5 |
| Scheduled End | Day 2.5 |

Files Added / Changed

- Edit: .github/workflows/deploy.yml (sed injection steps)

- GitHub: add 6 repository secrets

Assumptions

GitHub Secrets UI is accessible. Firebase config values from T1.3 are available.

AI Prompt for Implementation

Update the GitHub Actions deploy.yml workflow to inject all 6 Firebase config fields from GitHub repository secrets into js/firebase-config.js using sed commands before the deployment step. Each placeholder in firebase-config.js follows the pattern __FIREBASE_FIELDNAME__. Also add instructions for adding the 6 secrets (FIREBASE_API_KEY etc.) to the GitHub repository settings.

| T1.8 | Create project directory structure and placeholder files | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | Spec Sec 2 |
| Dependencies | T1.1 |
| Scheduled Start | Day 0.5 |
| Scheduled End | Day 1.0 |

Files Added / Changed

- Create: index.html, css/styles.css, css/table.css

- Create: js/app.js, js/auth.js, js/firestore.js

- Create: js/exercises.js, js/scheduler.js, js/logger.js

- Create: js/history.js, js/progression.js, js/ui.js

- Create: .gitignore, firebase-config.js (placeholders)

Assumptions

Repository from T1.1 is cloned locally. VS Code is available.

AI Prompt for Implementation

Create the full directory and file structure for the postopExerciseTracker project as specified in the Functional Specification Section 2. All JS files should contain a single comment line indicating their purpose. The firebase-config.js file should export a firebaseConfig object with 6 fields set to placeholder strings in the format __FIREBASE_FIELDNAME__ (e.g. __FIREBASE_API_KEY__).

| T1.9 | Verify end-to-end deployment: push to main → GitHub Pages live | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 1 — Project Setup & Infrastructure |
| Requirement IDs | M-24 |
| Dependencies | T1.7, T1.8 |
| Scheduled Start | Day 2.5 |
| Scheduled End | Day 3.0 |

Files Added / Changed

- Edit: index.html (add 'Hello World' test content)

- Verify: https://perelgut.github.io/postopExerciseTracker/ loads

Assumptions

T1.7 and T1.8 are complete. GitHub Actions workflow runs on push.

AI Prompt for Implementation

[Manual verification step] Commit and push all placeholder files to main. Verify the GitHub Actions workflow runs successfully and the site loads at https://perelgut.github.io/postopExerciseTracker/. No AI prompt required.

| T2.1 | Author exercises.js — all 11 exercises, all progressions, all descriptions | Duration: 2d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-01 to M-05, M-13 |
| Dependencies | T1.8 |
| Scheduled Start | Day 1.0 |
| Scheduled End | Day 3.0 |

Files Added / Changed

- Edit: js/exercises.js — full EXERCISES array with all 11 exercises and progressions

Assumptions

exercises.js author has the corrected spreadsheet (Ex 7 = 4 progressions). All descriptions are final.

AI Prompt for Implementation

Write the complete exercises.js file for the postopExerciseTracker application. The file must export a const EXERCISES array containing 11 exercise objects. Each object has fields: id (integer 7-17), name (string), displayName (e.g. 'Ex 7: Bridge'), frequency ('Daily'¦'Alt1'¦'Alt2'), maxProgression (integer), and progressions (array of objects with fields: level, description, type ('Rep'¦'Time'), defaultCount, defaultRepeats). Use the exact exercise data from the Functional Specification Section 3.1 and the Requirements Document Section 3. Exercise 7 must have 4 progressions (0-3).

| T2.2 | Author firebase-config.js with placeholder tokens | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-15 |
| Dependencies | T1.7 |
| Scheduled Start | Day 2.5 |
| Scheduled End | Day 3.0 |

Files Added / Changed

- Edit: js/firebase-config.js — __PLACEHOLDER__ tokens for all 6 config fields

Assumptions

Firebase config values from T1.3 are known. Placeholder format __FIREBASE_FIELDNAME__ is consistent with deploy.yml.

AI Prompt for Implementation

Write the js/firebase-config.js file that imports the Firebase SDK modules (app, auth, firestore) and initialises the Firebase app using a firebaseConfig object. All 6 config values must use placeholder strings in the format __FIREBASE_FIELDNAME__ (e.g. __FIREBASE_API_KEY__). Export the initialised auth and db (Firestore) instances.

| T2.3 | Implement auth.js — Firebase Anonymous Auth, localStorage UID fallback | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-16,M-17 |
| Dependencies | T2.2 |
| Scheduled Start | Day 3.0 |
| Scheduled End | Day 4.0 |

Files Added / Changed

- Edit: js/auth.js — signInAnonymously(), localStorage UID storage/retrieval

Assumptions

Firebase SDK is available via CDN in index.html. T2.2 is complete.

AI Prompt for Implementation

Write the js/auth.js module for the postopExerciseTracker app. It must: (1) call Firebase signInAnonymously() on init, (2) on success store the UID in localStorage under key 'postop_uid', (3) on subsequent loads check localStorage for existing UID and use Firebase auth state persistence, (4) export a function getCurrentUID() that returns the current anonymous UID, (5) handle auth errors gracefully with a user-facing error message.

| T2.4 | Implement firestore.js — all Firestore read/write functions | Duration: 2d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-15,M-18 |
| Dependencies | T2.3 |
| Scheduled Start | Day 4.0 |
| Scheduled End | Day 6.0 |

Files Added / Changed

- Edit: js/firestore.js — saveLogEntry(), updateLogEntry(), getLogs(), getProfile(), saveProfile(), getProgressions(), updateProgression()

Assumptions

T2.3 is complete. Firestore security rules from T1.6 are applied.

AI Prompt for Implementation

Write the js/firestore.js module for the postopExerciseTracker app. It must export these async functions: saveLogEntry(uid, dateStr, entry), updateLogEntry(uid, dateStr, exerciseId, updatedEntry), getLogs(uid, dateStrings[]), getProfile(uid), saveProfile(uid, profileData), getProgressions(uid), updateProgression(uid, exerciseId, newLevel). All Firestore paths follow the schema in Functional Specification Section 3.2. Enable Firestore offline persistence. Handle all errors and return {success, error} objects.

| T2.5 | Implement scheduler.js — getApplicableExercises(), day-of-week rules | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-10 |
| Dependencies | T2.1 |
| Scheduled Start | Day 3.0 |
| Scheduled End | Day 4.0 |

Files Added / Changed

- Edit: js/scheduler.js — getApplicableExercises(date), ALT1_DAYS, ALT2_DAYS constants

Assumptions

T2.1 is complete. EXERCISES array structure is final.

AI Prompt for Implementation

Write the js/scheduler.js module. Export one function: getApplicableExercises(date, exercises). date is a JavaScript Date object. exercises is the EXERCISES array from exercises.js. The function returns a filtered array of exercises applicable on that day of the week: ALT1_DAYS = [1,3,5] (Mon/Wed/Fri) return Daily + Alt1; ALT2_DAYS = [2,4,6] (Tue/Thu/Sat) return Daily + Alt2; Sunday (0) returns Daily only.

| T2.6 | Implement progression.js — read/write progressions, max validation | Duration: 1d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-12,M-13,M-14 |
| Dependencies | T2.4 |
| Scheduled Start | Day 6.0 |
| Scheduled End | Day 7.0 |

Files Added / Changed

- Edit: js/progression.js — getCurrentProgression(), advanceProgression(), max validation

Assumptions

T2.4 and T2.5 are complete.

AI Prompt for Implementation

Write the js/progression.js module. It must maintain an in-memory progressions cache (populated on app startup from Firestore). Export: getCurrentProgression(exerciseId), advanceProgression(exerciseId, uid) which validates against the exercise's maxProgression before writing to Firestore via firestore.js, and initProgressions(uid) which loads progressions from Firestore into the cache.

| T2.7 | Unit test: scheduler.js (all 7 days, verify correct exercise sets) | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-10 |
| Dependencies | T2.5 |
| Scheduled Start | Day 4.0 |
| Scheduled End | Day 5.0 |

Files Added / Changed

- No file changes — manual or scripted test of scheduler.js for all 7 days

Assumptions

T2.5 is complete. Developer has browser console access.

AI Prompt for Implementation

[Manual test step] Open the browser console and test scheduler.js for all 7 days of the week. For each day, call getApplicableExercises(testDate, EXERCISES) and verify the returned exercise IDs match the expected sets from Functional Specification Section 4.1.

| T2.8 | Unit test: progression.js (boundary values, max progression enforcement) | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-12,M-13 |
| Dependencies | T2.6 |
| Scheduled Start | Day 7.0 |
| Scheduled End | Day 7.5 |

Files Added / Changed

- No file changes — manual test of progression.js boundary values

Assumptions

T2.6 is complete.

AI Prompt for Implementation

[Manual test step] Test progression.js boundary conditions: attempt to advance an exercise already at maxProgression and verify it is blocked. Verify all 11 exercises initialise at progression 0.

| T2.9 | Integration test: auth + Firestore read/write round-trip | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 2 — Data Layer |
| Requirement IDs | M-15,M-16 |
| Dependencies | T2.4 |
| Scheduled Start | Day 6.0 |
| Scheduled End | Day 7.0 |

Files Added / Changed

- No file changes — integration test: auth flow + Firestore read/write in browser console

Assumptions

T2.4 is complete. Live Firebase project is accessible.

AI Prompt for Implementation

[Manual integration test] In the browser with the app loaded, open the console and: (1) verify signInAnonymously() returns a UID, (2) verify the UID is stored in localStorage, (3) call saveLogEntry() with test data and verify the document appears in the Firebase Console, (4) call getLogs() and verify the data is returned correctly.

| T3.1 | Implement index.html shell, CSS styles.css — mobile-first layout | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-23 |
| Dependencies | T1.8 |
| Scheduled Start | Day 1.0 |
| Scheduled End | Day 2.0 |

Files Added / Changed

- Edit: index.html — full SPA shell with 4 screen divs

- Edit: css/styles.css — mobile-first base styles, bottom nav, card styles

Assumptions

T1.8 is complete. No CSS framework — vanilla CSS only.

AI Prompt for Implementation

Write the index.html file for the postopExerciseTracker SPA. It must include: a <head> with viewport meta tag and links to css/styles.css and css/table.css; a <body> with 4 screen divs (screen-loading, screen-log, screen-history, screen-progressions), each initially hidden except screen-loading; script tags loading the Firebase SDK from CDN, then all js/ modules in dependency order. Write the css/styles.css file with mobile-first responsive styles: base font size 16px, max-width 600px centred, card component styles with border and padding, bottom nav bar fixed to viewport bottom.

| T3.2 | Implement ui.js — screen switching, toast notifications, loading spinner | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | Spec Sec 5 |
| Dependencies | T3.1 |
| Scheduled Start | Day 2.0 |
| Scheduled End | Day 3.0 |

Files Added / Changed

- Edit: js/ui.js — showScreen(), toast(), showLoading(), hideLoading(), toggleDescription()

Assumptions

T3.1 is complete.

AI Prompt for Implementation

Write the js/ui.js module. Export: showScreen(screenId) which hides all screens and shows the target; toast(message, type) which shows a floating notification (success=green, error=red) for 2.5 seconds; showLoading() / hideLoading() which shows/hides the screen-loading spinner; toggleDescription(exerciseId) which expands or collapses the description text for an exercise card.

| T3.3 | Implement app.js — startup sequence (Steps 1–9 per Spec Sec 6.1) | Duration: 1.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-18, Spec 6.1 |
| Dependencies | T2.4, T2.5, T3.2 |
| Scheduled Start | Day 6.0 |
| Scheduled End | Day 7.5 |

Files Added / Changed

- Edit: js/app.js — full 9-step startup sequence

Assumptions

T2.3, T2.4, T2.5 are complete. T3.2 is complete.

AI Prompt for Implementation

Write the js/app.js module implementing the 9-step startup sequence from Functional Specification Section 6.1. Steps in order: show loading screen, load Firebase config, call auth.js signIn, store UID to localStorage, fetch/create Firestore profile (set Day 1 if new), fetch progressions, call scheduler.js for today's exercise list, fetch today's log document, hide loading and show screen-log. Handle each step's failure case as specified.

| T3.4 | Implement bottom navigation bar (Today / History / Progress tabs) | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | Spec Sec 5.5 |
| Dependencies | T3.2 |
| Scheduled Start | Day 3.0 |
| Scheduled End | Day 3.5 |

Files Added / Changed

- Edit: index.html — bottom nav bar HTML

- Edit: css/styles.css — nav bar styles, active tab highlight

Assumptions

T3.1 and T3.2 are complete.

AI Prompt for Implementation

Add the bottom navigation bar HTML to index.html with three buttons: Today (links to screen-log), History (screen-history), Progress (screen-progressions). Add CSS to css/styles.css for the nav bar: fixed position bottom:0, full width, flex layout, minimum tap target height 56px, active tab highlighted in blue.

| T3.5 | Implement screen-log: exercise cards, expand/collapse, frequency badges | Duration: 2d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-01 to M-05 |
| Dependencies | T3.3, T2.1 |
| Scheduled Start | Day 7.5 |
| Scheduled End | Day 9.5 |

Files Added / Changed

- Edit: index.html — screen-log div structure

- Edit: js/logger.js — renderExerciseCards(), toggleCard()

- Edit: css/styles.css — card styles, badge styles

Assumptions

T2.1, T3.3, T3.4 are complete.

AI Prompt for Implementation

Write the exercise card rendering logic in js/logger.js. The function renderExerciseCards(exercises, todayLog, progressions) renders one card per exercise into screen-log. Each card shows: displayName (bold, tappable), frequency badge (colour-coded: Daily=green, Alt1=blue, Alt2=orange), progression badge ('Prog N'). Clicking the name calls ui.js toggleDescription() to expand/collapse the description. Exercises already logged show a green tick and saved values. Use the EXERCISES data from exercises.js.

| T3.6 | Implement screen-log: time-of-day selector with device clock pre-selection | Duration: 1d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-09 |
| Dependencies | T3.5 |
| Scheduled Start | Day 9.5 |
| Scheduled End | Day 10.5 |

Files Added / Changed

- Edit: js/logger.js — getTimeOfDayBucket(hour), pre-select dropdown on render

Assumptions

T3.5 is complete.

AI Prompt for Implementation

Add the time-of-day selector to the screen-log. It is a <select> dropdown with 8 options matching the time buckets from Requirements M-09. Write a function getTimeOfDayBucket(hour) that maps the current device hour (0-23) to the correct bucket string, and pre-selects the dropdown on render. The patient can change the selection at any time.

| T3.7 | Implement logger.js — log entry capture, validation, Firestore save | Duration: 1.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-06 to M-08 |
| Dependencies | T3.5, T2.4 |
| Scheduled Start | Day 9.5 |
| Scheduled End | Day 11.0 |

Files Added / Changed

- Edit: js/logger.js — captureLogEntry(), validateInputs(), saveEntry() calling firestore.js

Assumptions

T3.5, T3.6, T2.4 are complete.

AI Prompt for Implementation

Write the log entry capture and save logic in js/logger.js. When the patient clicks 'Log' on an exercise card: (1) read count and repeats input values, (2) validate both are non-negative integers, (3) build an entry object with exerciseId, progressionLevel, timeOfDay (from selector), count, repeats, loggedAt timestamp, (4) call firestore.js saveLogEntry(), (5) on success update the card to show logged state with green tick, (6) on failure show error toast.

| T3.8 | Implement edit/update existing log entry (same day) | Duration: 1d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | S-02 |
| Dependencies | T3.7 |
| Scheduled Start | Day 11.0 |
| Scheduled End | Day 12.0 |

Files Added / Changed

- Edit: js/logger.js — editEntry(), updateEntry() — re-open card in edit mode

Assumptions

T3.7 is complete.

AI Prompt for Implementation

Add edit functionality to js/logger.js. When a patient taps a card already in logged state, reopen it in edit mode pre-filled with the saved count and repeats. Show an 'Update' button instead of 'Log'. On Update: call firestore.js updateLogEntry() with the new values. On success: return to logged state with updated values.

| T3.9 | Implement screen-progressions: all 11 cards, Advance button, max guard | Duration: 1.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-12 to M-14 |
| Dependencies | T3.2, T2.6 |
| Scheduled Start | Day 7.0 |
| Scheduled End | Day 8.5 |

Files Added / Changed

- Edit: index.html — screen-progressions div

- Edit: js/progression.js — renderProgressionCards(), handleAdvance()

Assumptions

T2.6, T3.2 are complete.

AI Prompt for Implementation

Write the screen-progressions UI. In index.html add the screen-progressions div. In js/progression.js add renderProgressionCards() which renders one card per exercise (all 11, regardless of day). Each card shows: displayName, current progression level, full description for current level (always expanded), and an 'Advance' button. The Advance button is disabled (greyed, cursor not-allowed) when currentLevel === maxProgression. Clicking Advance calls advanceProgression() and re-renders the card.

| T3.10 | Implement history.js — 30-day table, sticky row header, horizontal scroll | Duration: 2d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-19 to M-22 |
| Dependencies | T3.2, T2.4, T2.5 |
| Scheduled Start | Day 6.0 |
| Scheduled End | Day 8.0 |

Files Added / Changed

- Edit: index.html — screen-history div

- Edit: js/history.js — buildHistoryTable(), getCellContent()

Assumptions

T2.4, T2.5, T3.2 are complete.

AI Prompt for Implementation

Write js/history.js. The function buildHistoryTable(uid) fetches the last 30 days of log documents from Firestore via firestore.js getLogs(), then builds the 30-day × 11-column table DOM in screen-history. For each cell: if exercise was not applicable that day (per scheduler.js) render a dimmed dot; if no entry render '—'; if skipped (count=0) render '0'; otherwise render three lines: 'P{level}', '{count}{r¦s}', '×{repeats}'.

| T3.11 | Implement css/table.css — table layout, cell formatting, responsive scroll | Duration: 1d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 3 — UI: Core Screens |
| Requirement IDs | M-19 to M-22, S-05 |
| Dependencies | T3.10 |
| Scheduled Start | Day 8.0 |
| Scheduled End | Day 9.0 |

Files Added / Changed

- Edit: css/table.css — table grid, cell 3-line format, sticky column, overflow-x scroll

Assumptions

T3.10 is complete.

AI Prompt for Implementation

Write css/table.css for the 30-day history table. Requirements: the date column (leftmost) must be sticky (position:sticky, left:0) so it stays visible when scrolling horizontally; the table container div must have overflow-x:auto; each data cell must display its three lines of content in a compact monospace-style format; column headers ('Ex 7' etc.) must be visible and not overlap. Minimum cell width 52px.

| T4.1 | Recovery day counter — calculate and display 'Day N' on screen-log | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | M-11, S-03 |
| Dependencies | T3.3 |
| Scheduled Start | Day 7.5 |
| Scheduled End | Day 8.0 |

Files Added / Changed

- Edit: js/app.js — compute recoveryDay from day1, inject into DOM

Assumptions

T3.3 is complete. day1 is stored in Firestore and in localStorage.

AI Prompt for Implementation

Add the recovery day counter to screen-log. In js/app.js after the profile is loaded, calculate recoveryDay = Math.floor((today - day1InMs) / 86400000) + 1 and update the 'Day N' label in the DOM. Format as 'Day 14 of recovery'.

| T4.2 | Completion indicator — green/amber badge showing today's log status | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | S-01 |
| Dependencies | T3.7 |
| Scheduled Start | Day 11.0 |
| Scheduled End | Day 11.5 |

Files Added / Changed

- Edit: js/logger.js — checkTodayComplete(), update completion badge in DOM

Assumptions

T3.7 is complete.

AI Prompt for Implementation

Add a completion indicator badge to the screen-log header. After all exercises for today are loaded: if all applicable exercises have a logged entry (count > 0), show a green checkmark badge; otherwise show an amber ring badge. The badge updates dynamically after each Log or Update action without requiring a page refresh.

| T4.3 | Offline banner — detect navigator.onLine, show/hide amber banner | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | S-04 |
| Dependencies | T3.2 |
| Scheduled Start | Day 3.0 |
| Scheduled End | Day 3.5 |

Files Added / Changed

- Edit: js/ui.js — offlineBanner(), online/offline event listeners

Assumptions

T3.2 is complete. Browser supports online/offline events.

AI Prompt for Implementation

Add offline detection to js/ui.js. Listen for window 'online' and 'offline' events. When offline, show an amber banner at the top of the screen reading 'You are offline. Exercises will sync when reconnected.' When back online, hide the banner and show a brief toast 'Back online — syncing.'

| T4.4 | Enable Firestore offline persistence (enablePersistence()) | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | S-04 |
| Dependencies | T2.4 |
| Scheduled Start | Day 6.0 |
| Scheduled End | Day 6.5 |

Files Added / Changed

- Edit: js/firestore.js — add enablePersistence() call during init

Assumptions

T2.4 is complete. Browser supports IndexedDB (all target browsers do).

AI Prompt for Implementation

Add Firebase Firestore offline persistence to js/firestore.js. Call enableIndexedDbPersistence(db) immediately after Firestore is initialised. Handle the 'failed-precondition' error (multiple tabs) and 'unimplemented' error (browser not supported) gracefully — log a warning but do not crash the app.

| T4.5 | Cross-browser testing: iOS Safari, Android Chrome, Desktop Chrome/Firefox/Edge | Duration: 1.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | M-23 |
| Dependencies | T3.10, T3.9, T3.7 |
| Scheduled Start | Day 11.0 |
| Scheduled End | Day 12.5 |

Files Added / Changed

- No file changes — test on physical/emulated devices

Assumptions

T3.10, T3.9, T3.7 are complete. Physical or emulated test devices are available.

AI Prompt for Implementation

[Manual test step — no code generated] Test the complete application on: (1) iPhone Safari (iOS 15+), (2) Android Chrome, (3) Desktop Chrome, (4) Desktop Firefox, (5) Desktop Edge. Document all issues found.

| T4.6 | Mobile layout review: 320px min-width, tap targets 44px, font sizes | Duration: 1d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | M-23, NFR |
| Dependencies | T4.5 |
| Scheduled Start | Day 12.5 |
| Scheduled End | Day 13.5 |

Files Added / Changed

- Edit: css/styles.css — fix any mobile layout issues found in T4.5

Assumptions

T4.5 testing is complete and issues are documented.

AI Prompt for Implementation

Based on issues found in T4.5, update css/styles.css and css/table.css to fix mobile layout problems. Ensure: all tap targets are at least 44×44px; base font size is at least 16px; no horizontal overflow on screen-log or screen-progressions; the history table scrolls correctly on mobile.

| T4.7 | End-to-end functional test: full patient session from Day 1 through history view | Duration: 1d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | All M-reqs |
| Dependencies | T4.5 |
| Scheduled Start | Day 12.5 |
| Scheduled End | Day 13.5 |

Files Added / Changed

- No file changes — scripted end-to-end test session

Assumptions

T4.5 and T4.6 are complete.

AI Prompt for Implementation

[Manual end-to-end test — no code generated] Perform a complete patient session test: (1) open app for first time (Day 1 set), (2) log all applicable exercises for today, (3) advance one progression, (4) open history table and verify today's row is populated, (5) simulate offline by disabling network and log an exercise, (6) re-enable network and verify sync. Document results.

| T4.8 | Bug fixes from T4.5–T4.7 testing | Duration: 1.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | All |
| Dependencies | T4.7 |
| Scheduled Start | Day 13.5 |
| Scheduled End | Day 15.0 |

Files Added / Changed

- Edit: multiple files — bug fixes identified in T4.5–T4.7

Assumptions

T4.7 test results are documented.

AI Prompt for Implementation

Fix all bugs identified in T4.5–T4.7 testing. Each fix should be a targeted edit to the relevant file(s). After each fix, re-verify the specific test case that failed.

| T4.9 | Author README.md — setup instructions, Firebase config steps, repo overview | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 4 — Integration, Polish & Should Haves |
| Requirement IDs | Spec Sec 2 |
| Dependencies | T1.9 |
| Scheduled Start | Day 3.0 |
| Scheduled End | Day 3.5 |

Files Added / Changed

- Edit: README.md — full setup guide

Assumptions

T1.9 is complete. All setup steps have been performed and are fresh in developer memory.

AI Prompt for Implementation

Write the README.md file for the postopExerciseTracker repository. Include: project description, live URL (https://perelgut.github.io/postopExerciseTracker/), Firebase setup instructions (7 steps from Functional Specification Section 8.1), GitHub Secrets setup instructions (6 secrets), local development instructions (no build step — open index.html directly or use a local HTTP server), and file structure overview.

| T5.1 | Final deployment to GitHub Pages — verify live at perelgut.github.io/postopExerciseTracker/ | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 5 — Release & Handover |
| Requirement IDs | M-24 |
| Dependencies | T4.8 |
| Scheduled Start | Day 15.0 |
| Scheduled End | Day 15.5 |

Files Added / Changed

- No file changes — push to main triggers GitHub Actions deploy

Assumptions

T4.8 is complete. All code is committed.

AI Prompt for Implementation

[Deployment step] Ensure all code is committed and pushed to main. Verify GitHub Actions workflow completes successfully. Confirm the live URL https://perelgut.github.io/postopExerciseTracker/ loads the app.

| T5.2 | Smoke test on live deployed URL — all screens, all exercises, Firestore writes | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 5 — Release & Handover |
| Requirement IDs | M-24 |
| Dependencies | T5.1 |
| Scheduled Start | Day 15.5 |
| Scheduled End | Day 16.0 |

Files Added / Changed

- No file changes — browser verification of live URL

Assumptions

T5.1 deployment is successful.

AI Prompt for Implementation

[Smoke test — no code generated] On the live deployed URL, verify: (1) app loads without console errors, (2) today's exercises display correctly, (3) logging an exercise saves to Firestore (verify in Firebase Console), (4) progression screen loads all 11 exercises, (5) history table loads. Document any failures.

| T5.3 | Patient handover — share URL, brief walkthrough of screens and progression management | Duration: 0.5d | ⚑ CRITICAL PATH |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 5 — Release & Handover |
| Requirement IDs | All |
| Dependencies | T5.2 |
| Scheduled Start | Day 16.0 |
| Scheduled End | Day 16.5 |

Files Added / Changed

- No file changes — patient walkthrough

Assumptions

T5.2 smoke test passed. Patient has a device with a browser.

AI Prompt for Implementation

[Patient handover — no code generated] Share the URL https://perelgut.github.io/postopExerciseTracker/ with the patient. Walk through: how to log daily exercises, how to advance a progression, how to view the history table, and what to do if the app shows an offline banner.

| T5.4 | Archive project documents (Requirements, Spec, Project Plan) to repo /docs folder | Duration: 0.5d | ◇ Non-critical |
| --- | --- | --- | --- |

| Field | Detail |
| --- | --- |
| Phase | Phase 5 — Release & Handover |
| Requirement IDs | — |
| Dependencies | T5.1 |
| Scheduled Start | Day 15.5 |
| Scheduled End | Day 16.0 |

Files Added / Changed

- Add: docs/Requirements_v1.1.docx, docs/FunctionalSpec_v1.1.docx, docs/ProjectPlan_v1.0.docx

Assumptions

T5.1 is complete. Document files are available locally.

AI Prompt for Implementation

Create a /docs folder in the repository and copy the three project documents into it: Requirements_v1.1.docx, FunctionalSpec_v1.1.docx, ProjectPlan_v1.0.docx. Commit and push.